## Project
Project Risk Register
The purpose of this Risk Register is to create a record of the envisaged challenges o delivery of the routes assessed in the Queensbury Tunnel Greenway Feasibility Study. This record will present the risks to completion, the locations along the route to which they apply, the potential consequences of the risk, and possible actions to overcome these challenges (if any).
Project: |  | Queensbury Tunnel Greenway Study
Compiled by: |  | KA
Checked by: |  | MT
Document ref: |  | 13358-N-RR-02-0000-00
Date Updated: |  | 2021-10-10
No. | Risk Cause | Risk Event | Locations within the Network | Impacts | Secondary effects | Possible actions
1 | Landowner issues including: - Requested compensation costs are too high - Refusal to support development of alignment - Alternative development progressed before delivery commences | Proposed alignment cannot be developed as designed. | Wherever the route crosses private land, there is a risk that landowner issues may occur. Land in possession of unknown landowners account for approximately between 30% to 45% of the overall route, dependent on route considered. | Critical: - Route as planned is incomplete, and fails to connect towns as intended - Integrity of proposed alignments reduced to achieve complete route Major: - Costs for land acquisition/access increase - Extended negotiations for acquisition/access - Further feasibility work required to revisit alternatives | Route is less attractive to users, resulting in lower usage than anticipated Negative publicity associated with delays/increased costs | Include alignments in RoW improvement plans. Include safeguarding of alignment in planning consent for development. Begin negotiating and engagement early in the delivery process.
2 | Ecological surveys return evidence of protected and priority species and sensitive habitats. | Licensing, compensation and mitigation required prior to construction. The requirement to achieve a 10% Biodiversity Net Gain (BNG) which must be maintained for 30 years. | All non-highway locations carry a risk of ecological complication. Non-highway locations account for approximately 50 - 75% of the overall route dependent on route choice. All non-highway locations carry a risk of ecological complication. Example of areas of higher ecological risk include: broadleaved deciduous woodland, lowland meadows, native hedgerows, tunnels, bridges, ponds and watercourses. Further details of potential ecological risks and constraints can be found in the Ecological desk study, Appendix F of the feasibility study. | Major: - Integrity of proposed alignments reduced to achieve complete route - Mitigation and compensation activity delays project delivery and increases costs - Specification and or construction methods require alteration to meet conditions imposed, with consequences for route character Opportunity: - Ecological mitigation and compensation enhances environment and biodiversity within corridors | Route is less attractive to users, resulting in lower usage than anticipated Negative publicity associated with delays/increased costs Ecological enhancement generates increased usage and support for route | Early consultation with relevant bodies to understand likely ecological requirements. Full ecological assessments carried out well in advance of final designs and planning submissions.The requirement to achieve BNG would be considered at an early stage. Rapid decision-making and delivery of Queensbury Tunnel alignment if selected, to avoid potential re-colonisation after stabilisation works complete.
3 | Future planning applications and development/re-development on or alongside alignments. | Development prevents delivery of proposed alignment. | Local plan development sites, areas with planning consent for development. | Critical: - Missing links introduced to alignment Moderate: - Alignment preserved, but with altered character | Route is less attractive to users, resulting in lower usage than anticipated | Include safeguarding of alignment in planning consent for development. Set out minimum specification required Engage early with proposed schemes that are situated on or along alignments.
4 | Cost estimates reflect high level of uncertainty for delivery. | Conservative cost estimates result in project being considered too expensive to undertake or; Unforeseen challenges result in underestimation of cost estimates despite conservative approach. | Applicable to whole network. | Critical: - Route is not progressed - Route is not completed Major: - Route is delivered at significantly greater cost than original estimates Moderate: - Route is delivered at a reduced specification to reduce costs | Public and political backlash directed at project client and project team Negative publicity associated with deviations from cost estimates Reduced specification introduces accessibility challenges for some users.
5 | TCF/ WT+TF routes are not delivered as expected | Proposed alignment cannot be developed as designed. | Thornton Road Highway Option Halifax to Holmfield Highway Option Halifax to Holmfield Greenway option: (H102 to H108) | Critical: - Route is incomplete, and fails to connect towns as intended Major: - Increased design and construction costs to deliver alignments | Route fails to generate assumed utility and longer distance recreational users
6 | TCF/WY+TF routes delivered in advance of wider alignments | Connectivity is judged to be provided | West Bradford Corridor, Halifax to Holmfield Corridor. | Major: - Greenway links are not delivered | Connectivity between Bradford and Clayton is not provided. Stakeholder dissatisfaction.
7 | Mass Transit proposals within study area. | Mass Transit delivery impacts on delivery of walking and cycling infrastructure within study area. | West Bradford Corridor Halifax to Holmfield Corridor Holmfield to Queensbury Corridor | Critical: - MTS delivery prevents completion of walking and cycling routes Major: - MTS delivery alters character of walking and cycling routes Opportunity: - MTS connectivity strengthens case for delivery of proposed alignments |  | Ensure representative for walking and cycling interests is included in MTS steering group.
8 | Creation of public rights of way | Public right of way creation and upgrade process results in delays to delivery | All non-highway locations where bridleway access is not already established. Summary maps showing creation and upgrade requirements are included in the feasibility report. | Major: - Rights of way not achieved. Opportunity: - Support for new rights of way demonstrated | Alignments reliant on permissive agreements, with risk of future rescindment. Compulsory orders required to achieve RoW with associated publicity challenges. Publicity during RoW process generates interest and support for routes, leading to community stewardship.
9 | Highway Adoption | Local Highway Authority do not adopt existing unadopted roads that have been improved in order to accommodate walking and cycling. | Station Road, Queensbury Hainworth Road, Keighley | Major: - Route is not maintained | Quality of experience diminishes over time, leading to declining usage numbers.
10 | Public response | Public disagrees with route choice or alignment proposals | Whole route | Major: - Public enquiries lead to delays to delivery and increased costs | Chosen option becomes undeliverable. Significant time required to explore options that may be more acceptable to the public
11 | Public response | Public support for route choice or alignment proposals | Whole route | Opportunity: - Financial support received from public donors - Support groups formed | Reduced financial and maintenance burden
12 | BCR values | BCR values are sole metric for delivery decision. | Whole route | Major: - BCR values do not meet threshold for delivery |  | Consider the route as Xkm of high quality walking and cycling infrastructure implemented.
13
14
15
16
17
18
19
20